## Sprint Trend Data
Story Points |  |  |  |  | Hours |  |  | Defects Counts
Sprint | Committed Story Points | Accepted Story Points | Added Story points | Descoped Strory Points | Available Capacity(Day 1) | Estimated Hours | Actual Hours | Defects Captured during sprint | Defects Captured after Sprints or PO verification
Sprint 1 | 23 | 23 | 0 | 0 | 250 | 100 | 130 | 20 | 10
Sprint 2 | 29 | 29 | 0 | 10 | 220 | 130 | 40 | 20 | 1
Sprint 3 | 34 | 34 | 0 | 0 | 240 | 190 | 190 | 10 | 0
Sprint 4 | 16 | 10 | 23 | 0 | 280 | 140 | 200 | 30 | 4
Sprint 5 | 30 | 25 | 0 | 15 | 230 | 200 | 189 | 5 | 1
Sprint 6 | 45 | 30 | 0 | 0 | 243 | 221 | 178 | 12 | 4
Sprint 7 | 30 | 29 | 0 | 0 | 226 | 220 | 215 | 22 | 6

## PO Groom Histrory
Backlog Health
Date on which backlog was checked for groomed stories | Story Points
2017-03-31 | 10
2017-04-10 | 25
2017-04-12 | 30
2017-04-17 | 45
2017-04-23 | 74
2018-03-24 | 83

## Definition
Team
Team Name | Agile Digest X
Commitment Reliability |  |  |  | Velocity
Level | from | To | Total | Upper Margin | Lower Margin
Red | 0% | 80% | 80% | 40% | 15%
Amber | 81% | 95% | 15%
Green | 96% | 100% | 5%
Capacity Utilization |  |  |  | Defect Leakage
Level | from | To | Total | Level | from | To | Total
Red | 0% | 60% | 80% | Green | 0% | 5% | 5%
Amber | 61% | 85% | 25% | Amber | 6% | 16% | 11%
Green | 86% | 100% | 15% | Red | 17% | 100% | 84%